## IT Deployment APR-2020
Not Yet Started
Ongoing
Completed
Lagging
IT Developement (Year: 2020-21) (Apr-2020)
Redeployment PR FTGS (Start Date: 20-03-2020) (Target Date: 15-04-2020) | OMS Reports (Start Date: 10-03-2020) (Target Date: 25-04-2020) | VMS (Start Date: 05-03-2020) (Target Date: 25-04-2020) | LMS (Start Date: 23-03-2020) (Target Date: 01-05-2020)
1 Requirement Gathering & Analysis (20-03-2020) (RG,PPS) | 1 Requirement Gathering & Analysis (10-03-2020) (PPS,KK) | 1 Requirement Gathering & Analysis (05-03-2020) (RG,PPS,KK) | 1 Requirement Gathering & Analysis (23-03-2020) (RG,PPS,KK)
2 Design (25-03-2020) (PPS,GB) | 2 Design (15-03-2020) (KK) | Design (10-03-2020) (PPS,KK) | Design (03-04-2020) (GB)
3 Implementation and Coding (15-04-2020) (PPS) | 3 Implementation and Coding (18-04-2020) (KK) | 3 Implementation and Coding (20-04-2020) (PPS,KK) | 3 Implementation and Coding (25-04-2020) (GB)
4 Testing (17-04-2020) (PPS) | 4 Testing (20-04-2020) (KK,RG) | 4 Testing (16-04-2020) (PPS,KK) | 4 Testing (27-04-2020) (GB,PPS,KK)
5 Deployment (19-04-2020) (PPS) | 5 Deployment (23-04-2020) (KK) | 5 Deployment (22-04-2020) (PPS,KK) | 5 Deployment (29-04-2020) (PPS,KK)
6 User Training (20-04-2020) (RG) | 6 User Training (24-04-2020) (RG) | 6 User Training (28-04-2020) (RG) | 6 User Training (30-04-2020) (RG)